## Tasks
S | Objective |  | Go? | Do | Task | Product | Done? | Responsible | Due Date
0 | Project Plan | 0.1 | TRUE | Research | Literature Papers | Google Docs | TRUE | Maria
|  | 0.2 | TRUE | Define | Tasks Definition | Tasks Sheet | TRUE | Matos
|  | 0.3 | TRUE | Define | Data flow & Ultimate Goal | S0 | TRUE | Both
|  | 0.4 | TRUE | Define | Clinical Background for Project | Introduction Report | TRUE | Both | 2020-05-11
1 | Raw Data Preparation | 1.1 | TRUE | Define | Necessary Raw Data Processing | S1 | TRUE | Maria | 2020-05-11
|  | 1.2 | TRUE | Code | LabVIEW EEG Simulation | .vi file | TRUE
|  | 1.3 | TRUE | Code | LabVIEW Signal Extract |  | TRUE
|  | 1.4 | TRUE | Code | Multisim EEG Import | .ms14 file | TRUE
|  | 1.5 | TRUE | Code | Multi EEG Simulation |  | TRUE |  | 2020-05-12
2 | Analog Processing | 2.1 | TRUE | Define | Circuit Design | S2 | TRUE | Matos | 2020-05-11
|  | 2.2 | TRUE | Code | Signal Amplification | Preliminary .ms14 file | TRUE
|  | 2.3 | TRUE | Code | Signal Filtering |  | TRUE
|  | 2.4 | TRUE | Code | Processed Signal Display |  | TRUE
|  | 2.5 | TRUE | Code | Merge EEG and Circuit | Final .ms14 file | TRUE
|  | 2.6 | TRUE | Code | Multi-Channel Circuit |  | TRUE
|  | 2.7 | TRUE | Code | Mutisim Co-simulation |  | TRUE
3 | Graphical User Interface | 3.1 | TRUE | Define | Necessary GUI Blocks | S3 | TRUE | Both | 2020-05-25
|  | 3.2 | TRUE | Code | LabVIEW EEG Acquisition | .vi file | TRUE
|  | 3.3 | TRUE | Code | EEG Power Spectrum Display |  | TRUE | Maria
|  | 3.5 | TRUE | Code | EEG Segmentation |  | TRUE
|  | 3.6 | TRUE | Code | EEG alpha, beta, tetha Display |  | TRUE
|  | 3.7 | TRUE | Code | EEG Maximums Calculation |  | TRUE
|  | 3.8 | TRUE | Code | EEG Co-simulation circuit |  | TRUE | Matos
|  | 3.9 | TRUE | Code | EEG final result |  | TRUE
|  | 3.1 | TRUE | Code | Final Aesthetics |  | TRUE
|  | 3.11 | TRUE | Code | Final Debugging & Tests |  | TRUE | Both
4 | Final Report | 4.1 | TRUE | Define | Global Structure | S4 | TRUE
|  | 4.2 | TRUE | Organize | Data Preparation | .docx & .pdf files | TRUE
|  | 4.3 | TRUE | Organize | BoM |  | TRUE
|  | 4.4 | TRUE | Write | Background Research |  | TRUE | Jorge | 2020-05-11
|  | 4.5 | TRUE | Write | Background NeuroMarketing |  | TRUE | Matos | 2020-05-11
|  | 4.6 | TRUE | Write | Materials Section |  | TRUE
|  | 4.7 | TRUE | Write | Results & Discussion Section |  | TRUE
|  | 4.8 | TRUE | Write | Conclusions |  | TRUE
|  | 4.9 | TRUE | Write | Final Text Review |  | TRUE
|  |  | TRUE | Organize | Final Formatting |  | TRUE

## DataFlow
S | 1 | 1 | 2 | 3 | 4 | Goal
Tool | LabVIEW EEG Simulation | LabVIEW Signal Extract | Multisim Proof of Concept | LabVIEW Processing | LabVIEW Fancy Display | Neuro Marketing
Output | EEG signal | signal export | analog theoretical processing | alpha, beta, tetha frquencies | scalp maps